**Virginia State Systemic Improvement Plan**

***State Identified Measurable Result****:* ***Increasing the percentage of infants and toddlers who substantially increase their rate of growth in the area of positive social-emotional skills (including social relationships) by the time they exit early intervention***

Broad Improvement Strategy 1: Identify and implement initial and ongoing eligibility determination and assessment for service planning practices related to social-emotional development that effectively inform eligibility decisions, the child outcome summary process, IFSP development and service delivery

|  |  |  |  | **Indicators of Success & Evaluation Plan** | |
| --- | --- | --- | --- | --- | --- |
| **Steps** | **Projected**  **Timelines** | **Who Will Work on This** | **Resources Needed and others who can help\*** | **Short-Term** | **Long-Term** |
| 1. Establish recommended and/or required practices for use of a social-emotional screening tool(s) as part of eligibility determination and for ongoing developmental monitoring | 2022 – 2024  Completed | State staff with stakeholder group | National resources and other states’ policies and practices | Practice Manual updated and available on ITCVA website | By 2026, monitoring and fidelity assessment indicate practitioners are using the recommended and/or required screening and assessment tools and practices consistently and as intended  Referrals of children experiencing or at high risk of social-emotional delays (e.g., CAPTA referrals) increase from 2022 – 2026  By 2026, establish baseline on Annual Family Survey for percent of families agreeing that their knowledge about importance of social-emotional skills has increased  Monitoring conducted in 2024 – 2026 indicates IFSP outcomes and services are informed by social-emotional screening and/or assessment results |
| 1. Establish recommended and/or required practices for use of a social-emotional assessment tool(s) as part of initial and ongoing child assessment and additional questions on the family assessment tool | 2022 – 2024  Completed | State staff with stakeholder group | National resources and other states’ policies and practices | Practice Manual updated and available on ITCVA website |
| 1. Develop recommended practices around including eligibility and/or assessment team members with Infant Mental Health or related expertise | 2023 - 2024  Completed | State staff with stakeholder group | National resources and other states’ policies and practices | Practice Manual updated and available on ITCVA website |
| 1. Examine inequities/bias in eligibility determination and assessment practices/tools | 2023  Completed | State staff with stakeholder group | National resources and tools; work from other states  DBHDS DEI Officer | Practice Manual updated, as needed, and available on ITCVA website  Necessary training and resources identified |
| 1. Explore screening or assessing for other factors that impact infants’ and toddlers’ social-emotional development, such as parental depression, anxiety, trauma, parent-child interaction, attachment and temperament | 2023 – 2024  Completed | State staff with stakeholder group | National resources and other states’ policies and practices  Early Impact Virginia Alliance | At least one resource is developed and posted to the ITCVA website to share the information gained and/or communicate new practices |
| 1. Develop, adopt or adapt educational resources and training in a variety of formats for families, other caregivers and referral sources – importance of positive social-emotional skills and social relationships, what is typical at each age level, and red flags | 2025 | State staff and New Path Family Support Director with stakeholder group | Learn the Signs Act Early tools and products  NICU Project documents  PEATC, Center for Family Involvement  Private agencies, independent contractors offering parent classes | Resource(s) available on ITCVA website and widely disseminated to relevant groups and individuals (e.g., referral sources, families and organizations that support families) |
| 1. Conduct outreach with targeted referral sources (e.g., CAPTA, domestic violence and other social service organizations) to strengthen relationships and streamline referral processes and information sharing, as needed, to ensure timely referrals for children with potentially delayed or atypical social-emotional development | 2025 | State staff and local systems | National resources and other states’ policies and practices  Learn the Signs Act Early team | Regional or statewide meeting notes indicate outreach to multiple targeted referral sources in all regions  Number of referrals from CAPTA and/or other targeted referral sources within 1 year of completing targeted outreach activities |
| 1. Once screening and assessment practices and tools are identified, develop an implementation plan including professional development activities and resources needed to support implementation | 2024 – 2025 | Professional development team with stakeholder input | National and other states’ resources  Publisher resources | Implementation steps in place and added to SSIP |
| 1. Gather baseline data on the following:  * How many children were found eligible based on only delayed or atypical social-emotional development * How many children were found eligible based on delayed or atypical social-emotional development combined with other areas of delay or atypical development * What factors or circumstances are associated with or lead to determining a child eligible based only on delayed or atypical social-emotional development | 2025 | Data Manager and Technical Assistance Consultants | TRAC-IT  Information from local systems | Baseline data is collected and shared in a monthly ITCVA update |
| 1. Consider automatic eligibility category(ies) for children at very high risk for social-emotional/infant mental health delays or disorders | 2025-2026 | State staff with stakeholder group | Information from other states  National research | Recommendations are made to VICC and State Lead Agency  State regulations and Practice Manual are updated if eligibility criteria are adjusted |
| 1. Develop/adapt/adopt and implement a fidelity measure and process for expected screening, eligibility and assessment practices | 2025 - 2026 | State staff with stakeholder group | National and other states’ resources | Fidelity tool and process in place and reflected in Practice Manual |
| 1. Identify and implement additional professional development and/or other supports needed to sustain the use of expected screening, eligibility and assessment practices with fidelity | 2025 - 2026 | State staff with stakeholder group | National and other states’ resources | Professional development and/or other supports are identified and the SSIP is updated to reflect additional activities, as needed |

**Virginia State Systemic Improvement Plan**

***State Identified Measurable Result*: *Increasing the percentage of infants and toddlers who substantially increase their rate of growth in the area of positive social-emotional skills (including social relationships) by the time they exit early intervention***

Broad Improvement Strategy 2: Identify and implement evidence-based service delivery practices to promote positive social-emotional development for all eligible infants and toddlers and provide effective intervention to address delays and concerns

|  |  |  |  | **Indicators of Success & Evaluation Plan** | |
| --- | --- | --- | --- | --- | --- |
| **Steps** | **Projected**  **Timelines** | **Who Will Work on This** | **Resources Needed and others who can help \*** | **Short-Term** | **Long-Term** |
| 1. Explore available evidence-based practices to support positive social-emotional development and social relationships (e.g., Pyramid Model, PIWI, FAN, DEC Recommended Practices) in order to identify a core practice that will be implemented statewide | 2022  Completed | State staff with stakeholder group | National and other states’ resources | Core evidence-based practice is identified | By 2026, monitoring and fidelity assessment indicate practitioners are using the identified evidence-based core service delivery practices consistently and as intended  By 2026, monitoring indicates an increase from 2022 in the percent of children whose IFSPs include an outcome or short-term goal supporting the child’s social-emotional development  By 2026, establish baseline on Annual Family Survey indicates for percent of families agreeing that they know how to help their child develop positive social and emotional skills |
| 1. Strengthen state practice manual language, guidance and support for documenting family outcomes on the IFSP and identifying services and supports (including less-common supports like infant massage, lactation consultant, etc.) to meet those outcomes | 2024 - 2025 | State staff with stakeholder group | National and other states’ resources | Practice Manual updated and available on ITCVA website |
| 1. Establish and implement practices for accessing clinical-level treatment, including evidence-based dyadic treatment, when needed (e.g., when to access, who determines the need, who provides it, etc.) | 2025 | State staff with stakeholder group | DBHDS Child and Family Services staff  National and other states’ resources | Practice Manual updated and available on ITCVA website |
| 1. Identify, and share statewide, strategies for using Infant or Early Childhood Mental Health endorsed practitioners, LCSWs and other mental health specialty providers effectively throughout the early intervention process to support children, families and other providers | 2024 - 2025 | State staff with stakeholder group | IECMH Advisory Group  National and other states’ resources | At least one resource is developed to share identified strategies with planners and practitioners |
| 1. Develop, adopt or adapt general educational resources in a variety of formats for families and other caregivers about how to support the child in developing positive social-emotional skills and social relationships | 2024 - 2025 | State staff and New Path Family Support Director with stakeholder group  Suspension/expulsion workgroup | Learn the Signs Act Early tools and products  PEATC, Center for Family Involvement | Resource(s) available on ITCVA website and widely disseminated to relevant groups and individuals  At least 3 different formats are available |
| 1. Once an evidence-based practice is identified for statewide use, develop an implementation plan including professional development activities and resources needed to support implementation | 2024  Completed | Professional development team with stakeholder input | National and other states’ resources  Publisher resources | Implementation steps in place |
| 1. Develop/adapt/adopt and implement a fidelity measure and process for expected service delivery practices | 2025 - 2026 | State staff with stakeholder group | National and other states’ resources | Fidelity tool and process in place and reflected in Practice Manual |
| 1. Identify and implement additional professional development and/or other supports needed to sustain the use of expected service delivery practices with fidelity | 2025 - 2026 | State staff with stakeholder group | National and other states’ resources | Professional development and/or other supports are identified and the SSIP is updated to reflect additional activities, as needed |

**Virginia State Systemic Improvement Plan**

***State Identified Measurable Result*: *Increasing the percentage of infants and toddlers who substantially increase their rate of growth in the area of positive social-emotional skills (including social relationships) by the time they exit early intervention***

Broad Improvement Strategy 3: Build a sufficient and sustainable workforce of highly effective practitioners with the core competencies necessary to implement the eligibility determination, assessment for service planning, and service planning and delivery practices identified in broad improvement strategies 1 and 2

|  |  |  |  | **Indicators of Success & Evaluation Plan** | |
| --- | --- | --- | --- | --- | --- |
| **Steps** | **Projected**  **Timelines** | **Who Will Work on This** | **Resources Needed and others who can help \*** | **Short-Term** | **Long-Term** |
| 1. Ensure all practitioners know they have a role in supporting positive social-emotional development and a nurturing caregiver-child relationship and have the training and tools to do that    * Foundational knowledge on social-emotional developmental milestones    * Foundational knowledge about impact of birthing individuals’ and other caregivers’ health, including mental health, birth history and adverse childhood events on child social-emotional skills and child development more broadly. And understanding how this information informs coaching practices.    * How to assess and talk to families about this area and about routines so it’s a conversation, not an interview.    * Importance of parent-child interaction    * Intervention strategies and knowing when to refer for more specialized treatment/intervention | 2022 – 2026  Completed for 2024 | Professional Development Team, IECMH Endorsement Coordinator, and Early Childhood Mental Health Coordinator | Early Impact Virginia Alliance  Learn the Signs Act Early Team  ACE Interface Presenters  DBHDS, CSB trainers and resources | At least 2 new professional development activities, resources or tools relevant to all EI practitioners are developed per year to address these topics  Evaluations of products and learning opportunities, when available, indicate at least 75% of participants/users gained knowledge and/or skills and plan to implement at least one new thing they learned | Number of IMH-endorsed practitioners working in Virginia’s early intervention system increases by 2026, based on data maintained by the IECMH Endorsement Coordinator  Every local system reports access to at least one LCSW, IECMH-endorsed practitioner or other mental health specialty provider by 2026 |
| 1. Maintain Virginia’s Infant Mental Health endorsement program, with an emphasis on ensuring those who complete the program feel competent and confident to work in EI and increasing the number of candidates who complete the endorsement process, maintain their endorsement and stay in Virginia’s early intervention system | 2022 – 2026  Completed for 2024 | IECMH Endorsement Coordinator and Early Childhood Mental Health Coordinator | VAIMH  Private business partners - scholarships | A written plan is in place to address the areas of emphasis  Percent of candidates who complete endorsement within expected timelines increases by 2024 |
| 1. Identify and implement strategies to reduce stress and support the well-being of Virginia’s early intervention practitioners and leaders | 2022  Completed | Early Childhood Mental Health Coordinator | National and other states’ resources | At least 2 new strategies are implemented in 2022 |
| 1. Identify and implement strategies to recruit and retain early intervention personnel with mental health expertise as well as personnel in other fields (OT, PT, SLP, education, etc.) with the knowledge and skills to support positive social-emotional development for all children  * Develop and implement marketing campaign for careers in EI * Target specific fields/groups to recruit to EI: SW, Psychologists, mental health workers, retirees, part-time, after school hours, nurses | 2022 – 2026 | Professional Development Team and Early Childhood Mental Health Coordinator | National and other states’ resources  Va-LEND | At least 2 new strategies are identified and implemented |
| 1. Strengthen Medicaid funding for early intervention by adding Infant or Early Childhood Mental Health endorsed candidates and others with appropriate mental health qualifications to the list of providers approved by the state Medicaid agency to deliver early intervention services and exploring options for reimbursement for services to the caregiver (based on family outcomes on the IFSP) | 2023 – 2025 | State staff | DMAS  National and other states’ resources  New expanded Medicaid benefits for adults | New provider categories are added |
| 1. Work with the state Medicaid agency to increase early intervention reimbursement rates overall and add licensed mental health professionals to Reimbursement Category 1 | 2024 – 2026 | State staff | DMAS  Possibly funding for a rate study | Rate study is completed |
| 1. Build reflective supervision capacity to support all providers, including Infant Mental Health Endorsement candidates | 2024 - 2025 | Professional Development Team, IECMH Endorsement Coordinator | Early Impact Virginia Alliance  National and other states’ resources | The percentage of EI practitioners for whom reflective supervision is available increases as reported in written surveys and/or verbal feedback in regional meetings |  |
| 1. Explore options, including a hub or shared services approach, for increasing access to Infant or Early Childhood Mental Health Endorsed practitioners and others with this expertise for all areas of the Commonwealth | 2024 – 2025 | State staff with stakeholder input | Early Impact Virginia Alliance  National and other states’ resources | At least one new option is piloted or implemented |  |
| 1. Package resources into an orientation checklist/toolkit for local systems to use when onboarding new providers and service coordinators to ensure consistent use of evidence-based screening, assessment and service delivery that supports positive social-emotional skills and social relationships | 2025 - 2026 | Professional Development Team | Existing resources | Orientation checklist is available on VEIPD website |  |

**Virginia State Systemic Improvement Plan**

***State Identified Measurable Result*: *Increasing the percentage of infants and toddlers who substantially increase their rate of growth in the area of positive social-emotional skills (including social relationships) by the time they exit early intervention***

Broad Improvement Strategy 4: Use data to understand the impact of our efforts to improve positive social-emotional skills and social relationships and identify additional improvement strategies.

|  |  |  |  | **Indicators of Success & Evaluation Plan** | |
| --- | --- | --- | --- | --- | --- |
| **Steps** | **Projected**  **Timelines** | **Who Will Work on This** | **Resources Needed and others who can help \*** | **Short-Term** | **Long-Term** |
| 1. Finalize the data model for the new statewide data system, ensuring collection of data and connections between data elements necessary to analyze child outcomes for a wide variety of subgroups | 2022  Completed | State Lead Agency (EI and IT staff) and  data system vendor with stakeholder input | Funding already allocated | Data model is complete | A new data system is implemented and addresses the agreed upon data collection and reporting needs  By 2026, meeting agendas, notes, presentations, and other documentation indicate that local system managers and state staff use the new data system to correlate child outcome data with other program and demographic data to identify successes and to plan and evaluate improvement efforts  Via regional and local meetings and report by Technical Assistance and Monitoring Consultants, all local system managers demonstrate by 2026 that they can use the new data system independently to correlate child outcome data with other program and demographic data in order to identify successes and to plan and evaluate improvement efforts  Monitoring of local systems indicate they use the data system on a routine schedule to monitor timely data entry, consistent data quality and completeness (percent of exiters) for the child outcomes |
| 1. Identify reports and ad hoc tools for the new statewide data system that will support easy reporting and analysis of child outcome data at the state and local data | 2022  Completed | State Lead Agency (EI and IT staff) and  data system vendor with stakeholder input | Funding already allocated | Reports and ad hoc functions identified |
| 1. Develop and deliver training on the new statewide data system to all users to ensure consistency of data entered as well as effective use of standard reports and ad hoc reporting functions | 2022  Completed | State Lead Agency (EI and IT staff) and  data system vendor | Funding already allocated | At least 3 training methods are used  Training is widely accessed by all user types  Training evaluations indicate at least 75% of participants who submit the post-training evaluation learned the basic skills needed to access and use the new data system and know where to go for additional information and support |
| 1. Implement the new data system statewide | 2022  Phase I Completed  Phase II  2023-2024  Completed | State Lead Agency (EI and IT staff) and  data system vendor | Support may be needed to assist some local systems with integrating their local EHR with the new state data system | Data system is live and accessible to all users – |
| 1. Develop and implement a schedule and process for state-level review and analysis of child outcome data from the new data system | 2025 | State TA and Monitoring Consultants and Data Manager | None | Schedule is in place and added to the Monitoring Manual |
| 1. Address analysis and use of local child outcomes data on increasing positive social-emotional skills (including social relationships) to support data quality and program improvement through structured support in regional meetings, statewide meetings, and/or webinars | 2023-2026  Completed for 2024 | State TA and Monitoring Consultants | Technology support for webinars from the VCU Partnership for People with Disabilities  DaSY and/or ECTA consultation on tools and data interpretation, as needed, to support State staff in helping local systems | Regional and statewide meeting agendas indicate child outcome data analysis and use, including data quality, are addressed with local system managers at least once a year through FFY 2025 |
| 1. Develop and implement a cyclical monitoring approach that includes monitoring related to Indicator 3A (positive social-emotional skills, including social relationships) | Begin implementation 2024  Completed | State TA and Monitoring Consultants with input from local system managers | National and other states’ tools and examples | Protocol is in place and sent to all local system managers |

\*Generally, funding is only listed in the Resources Needed if there is an anticipated need for new or additional funding.